## Sheet2
Task | Day1 | Day2 | Day3 | Day4 | Day5 | Total Hours
implement Faculty Member info UI | 1 | 0 | 0 | 0 | 0 | 2
implement Secondary Faculty Member info UI | 2 | 0 | 1 | 0 | 0 | 2
implement Grad Student/Post Doc info UI | 0 | 2 | 0 | 0 | 0 | 2
implement Apprenticeship info UI | 1 | 0 | 3 | 0 | 0 | 4
implement Financial info UI | 0 | 0.5 | 0.5 | 0 | 0 | 1
implement Financial info UI | 0.5 | 0 | 0 | 0 | 0 | 1
implement Other info UI | 0 | 0 | 0 | 0 | 1 | 2
validate Faculty Member info | 1 | 0 | 0 | 0 | 1 | 2
validate Secondary Faculty Member info | 0 | 0 | 1 | 0 | 1 | 2
validate Grad Student/Post Doc info | 0 | 0 | 0 | 0 | 1 | 4
validate Apprenticeship info | 0 | 0 | 0 | 0 | 0 | 1
validate Financial info | 0 | 0 | 2 | 0 | 1 | 1
validate Other Info UI | 0 | 0 | 0 | 0 | 2.5 | 1
configure Project Form submission |  | 0 | 0 | 2.5 | 1 | 4
persist Project Form data to database | 0 | 0 | 0 | 4 | 1 | 1
create endpoint for Project Form | 0 | 0 | 0 | 0 | 1.5 | 1
create endpoint for Projects List | 1 | 1 | 0 | 0.5 | 0.3 | 2
retrieve Projects info form database | 0 | 0 | 0 | 2 | 0 | 2
create Projects List UI | 0 | 1.5 | 0 | 0 | 0 | 2
implement Student Demographic info UI | 0 | 0 | 0 | 1.2 | 0 | 2
implement Student Boulder contact information UI | 0 | 0 | 0 | 0.5 | 0 | 1
implement Student summer contact information | 0 | 0 | 0 | 0.5 | 0 | 1
implement Academic information UI | 0 | 0 | 0 | 0.5 | 0 | 2
implement Apprenticeship info UI | 0 | 0 | 1 | 0 | 0 | 4
implement Skills, Resume and other UI | 0 | 0 | 1 | 0 | 0 | 3
create endpoint for Student Application form | 0 | 0 | 0 | 0 | 1 | 1
Total | [5 empty] | 51
Actual remaining hours | 44.5 | 39.5 | 30 | 18.3 | 12.3